## Sheet1
Bug ID | Module | Severity | Priority | Title | Steps to Reproduce | Expected Result | Actual Result | Status
SM-001 | Student & Staff Mgmt | Major | High | Duplicate student profile allowed | Add student with existing ID and save | System should block duplicate profiles | Duplicate profile created | New
SM-002 | Student & Staff Mgmt | Minor | Medium | Invalid phone number accepted | Enter letters in phone field and save | Phone number format should be validated | Invalid phone accepted | New
SM-003 | Student & Staff Mgmt | Major | High | Staff profile saved without mandatory fields | Leave mandatory fields empty and save | Mandatory fields should be required | Profile saved with empty fields | New
SM-004 | Student & Staff Mgmt | Minor | Low | Address field allows special characters | Enter special characters in address field | Only valid characters allowed | Special characters accepted | New
CE-001 | Course & Enrollment | Major | High | Student enrolled in two classes for same subject | Enroll same student in two classes | Duplicate enrollment should be prevented | Student enrolled twice | New
CE-002 | Course & Enrollment | Major | Medium | Teacher assignment not updated after change | Change teacher and refresh page | Teacher assignment should update | Teacher assignment unchanged | New
CE-003 | Course & Enrollment | Minor | Low | Course deletion does not prompt confirmation | Delete course without confirmation | Confirmation popup should appear | Course deleted immediately | New
AT-001 | Attendance | Critical | High | Attendance not updating after edit | Edit previous attendance and save | Attendance should update correctly | Attendance not updated | New
AT-002 | Attendance | Major | High | Monthly attendance summary mismatch | Compare daily vs monthly summary | Monthly summary should be accurate | Summary incorrect | New
AT-003 | Attendance | Minor | Low | Absent students marked as present on refresh | Mark absent, refresh page | Absent status should persist | Status resets to present | New
AT-004 | Attendance | Major | Medium | Attendance can be submitted twice | Submit attendance twice | System should prevent duplicate submission | Attendance saved twice | New
GE-001 | Grading System | Major | High | Incorrect grade calculation when weight >100% | Create grade weights over 100% | System should validate weight limits | Incorrect grade calculated | New
GE-002 | Grading System | Minor | Low | Grade rounding issue in final score | Enter decimal marks and generate grade | Grade should round correctly | Incorrect rounding | New
GE-003 | Grading System | Major | Medium | Marks accepted beyond maximum limit | Enter marks above maximum | Marks should not exceed limit | Marks accepted | New
RG-001 | Report Generation | Major | Medium | Attendance summary missing in report card | Generate report card PDF | Attendance summary should appear | Attendance missing | New
RG-002 | Report Generation | Minor | Low | Teacher comments cut off in PDF | Add long teacher comment and export | Full comment should be visible | Comment truncated | New
RG-003 | Report Generation | Minor | Low | Report generation slow for large classes | Generate reports for large class | Report should generate efficiently | System slows down | New
IC-001 | Communication Portal | Critical | High | Parents cannot view teacher messages | Teacher sends message, parent logs in | Message should appear for parent | No message visible | New
IC-002 | Communication Portal | Major | Medium | Announcement visible to wrong user group | Send announcement to teachers only | Only selected users see announcement | Students see announcement | New
IC-003 | Communication Portal | Minor | Low | Old messages not sorted by date | View old messages | Messages sorted by latest | Messages unsorted | New